## Sheet1
MDR / IVDR - IMPLEMENTATION ROLLING PLAN (public) This Rolling Plan contains the list of identified essential implementing acts and actions to be put in place by the Commission during the transitional period together with relevant information on expected timelines and state-of-play. The information is organised into two main sections (implementing acts and other actions/initiatives). The document will be subject to quarterly review in order to provide the authorities and stakeholders with the most updated information. This document shall be read in conjunction with the “MDR/IVDR roadmap”, produced by the Competent Authorities for Medical Devices project (CAMD) in cooperation with the Commission (and available at https://www.camd-europe.eu/regulatory/medical-devices-regulation-vitro-diagnostics-regulation-mdr-ivdr-roadmap), which contains a much more comprehensive overview of all the initiatives (including guidance) expected to be undertaken during the transitional period by the Commission and the National Competent Authorities
Latest update: November 2018
No. | Subject | Legal basis | Description | Expected timelines (expected date of final adoption/date of acconmplishment) | State-of-play/Next step
IMPLEMENTING REGULATIONS/ACTS
1 | Notified bodies scope of designation | Article 42(13) MDR Article 38(13) IVDR | Implementing Act Definition of the list of codes and corresponding types of devices for the purpose of specifying the scope of the designation of notified bodies. This action is an essential pre-condition for the launch of the designation procedure for Notified Bodies | 26 November 2017 (Legal deadline) | Adopted and published on 24 November 2017 COMPLETED
2 | Reprocessing of single-use medical devices | Article 17(5) MDR | Implementing Act Common specifications laying down requirements related to reprocessing of single-use devices concerning: — risk management, including the analysis of the construction and material, related properties of the device (reverse engineering) and procedures to detect changes in the design of the original device as well as of its planned application after reprocessing, — the validation of procedures for the entire process, including cleaning steps, — the product release and performance testing, — the quality management system, — the reporting of incidents involving devices that have been reprocessed, and — the traceability of reprocessed devices. | November 2019 It shall be noted that, in the event that those CS are not adopted by 26 May 2020, reprocessing shall be performed in accordance with any relevant harmonised standards and national provisions that cover the aspects | Formal public consultation (Q2 2019)
3 | Common specifications for products without a medical purpose | Articles 1(2) and 9(1) MDR | Implementing Act Common specifications (CS) addressing for any of the groups of products listed in Annex XVI of the MDR, at least, application of risk management as set out in Annex I and, where necessary, clinical evaluation regarding safety. Application of MDR to Annex XVI products depends on the adoption of CS. | November 2019 | Informal consultation with National Competent Authorities and stakeholders on a draft text to be launched by beginning 2019
4 | Setting up of expert panels | recital 94 Article 106(1) MDR | Implementing Act (no comitology involved) Making provision for expert panels to be designated. Based on this implementing act, the selection of experts will be carried out. Expert panels are tasked inter alia with the delivery of opinions on the clinical evaluation of certain high-risk devices in the context of the pre-market scrutiny. Tasks of expert panels are described in Article 106(10). | Q3 2019 | Survey with MDCG members and stakeholders finalised. This is intended to support the drafting of the future act.
5 | Setting up of expert laboratories | Article 106(7) MDR | Implementing Act (no comitology involved) Designation of expert laboratories. Tasks of expert laboratories are described in Article 106(7). It shall be noted that the designation of expert laboratories is not mandatory. | TBD (not before 2020) | Survey with MDCG members and stakeholders finalised. While the issue of expert laboratories is under investigation, the appointment of expert laboratories does not constitute a priority
6 | Setting up of new structures under IVDR: - EU reference laboratories | recital 94 Articles 48(6), 100(1) and (3) IVDR | Implementing Act (no comitology involved) Designation of EU reference laboratories, active in the IVD field. Tasks are described in Article 100 | Q4 2019/Q1 2020 | Survey with MDCG members and stakeholders finalised. This is intended to support the drafting of the future act.
7 | Rules to facilitate fulfilment of tasks by EU reference laboratories and to ensure their compliance with criteria | Article 100(8)(a) | Implementing Act Rules to facilitate application of IVDR Article 100 (2) listing the tasks of the EURLs; rules to ensure compliance with criteria for an EURL listed in IVDR Article 100 (4) | Q4 2019/Q1 2020 | Survey with MDCG members and stakeholders finalised. This is intended to support the drafting of the future act.
8 | Fees for expert panel services | Article 106(13) MDR | Implementing Act Definition of fees for the advice provided by expert panels | Q4 2019 | Survey with MDCG members and stakeholders finalised. This is intended to support the drafting of the future act.
9 | Fees for EURL services | Article 100(8)(b) IVDR | Implementing Act Definition of fees for the advice/testing activities performed by EURL | Q2 2020 | Survey with MDCG members and stakeholders finalised. This is intended to support the drafting of the future act.
10 | Unique Device Identification (UDI) System: designation of issuing entities | recital 94 Article 27(2) MDR recital 94 Article 24(2) IVDR | Implementing Act (no comitology involved) Designation of one or more entities to operate a system for assignment of UDIs (‘issuing entity’). | May 2019 | Work ongoing on the call for application. Call for application expected to be published Q4 2018.
11 | EUDAMED | Article 33(8) MDR Article 30(1) IVDR | Implementing Act Definition of detailed arrangements necessary for the setting up and maintenance of Eudamed. This IA is mainly related to support, change management and maintenance rules | Q4 2019 | Implementation plan delivered on 26 May 2018. Work ongoing on the determination of functional specifications
12 | Common specifications for IVD Class D | Article 9 and 48(6) IVDR | Implementing Act/s Common Specifications for IVD Class D in the context of the scrutiny mechanism for high risk devices | Q4 2019 | As soon as the last Common Technical Specifications are adopted under the current Directive 98/79/EC (adoption expected Q1 2019), the new Common Specifications under the Regulation will be drafted
ACTIONS/INITIATIVES (OTHER THAN IMPLEMENTING REGULATIONS/ACTS)
1 | Notified Bodies designation |  | Designation of Notified Bodies under the MDR and IVDR. Designation of Notified Bodies under the Regulations is a pre-condition for carrying out of conformity assessments under the new Regulations | As many Notified Bodies as possible designated prior to May 2020 | As of end of November 2018, 35 applications received by the Commission services, 25 joint assessments scheduled. Full scope of MDR and IVDR covered in the applications
2 | EUDAMED: Implementation plan | Article 34(1) MDR | Plan for the implementation of the functional specifications for Eudamed to be drafted by the Commission. | Legal deadline for first release: 26 May 2018. | First release done in due time (25 May), work in progress for further releases COMPLETED
3 | EUDAMED: drawing up of functional specifications | Article 34(1) MDR | Functional specifications for Eudamed, to be drawn up by the Commission, in cooperation with the MDCG. | Q4 2018 | Work in progress
4 | EUDAMED: Audit of functional specifications | Article 34(2) MDR | Independent audit report based on which the Commission shall inform the MDCG when it has verified that Eudamed has achieved full functionality and meets the drawn up functional specifications | Audit to start in Q3/Q4 2019. Must be finalised by Q1 2020. | First analysis of type of contract done. Contract content to be determined as from beginning 2019
5 | EUDAMED go-live | Article 34 MDR | Eudamed may go-live from the moment a notice is published in the Official Journal of the European Union after a positive independent audit was performed that satisfies the MDCG | Notice to be published by 25 March 2020 | Work in progress to elaborate functional specifications and implement them
6 | EUDAMED: Setting of helpdesk | MDR Art 33(8) | Detailed arrangements necessary for the setting up and maintenance of Eudamed means at least the setting of an helpdesk/application support for Eudamed (normal IT good practice and implementing act obligation). | Before Eudamed go-live (March 2020) | Not started yet
7 | Communication campaign |  | In order to avoid bottle necks and to ensure access to medical devices, a communication campaign targeting all stakeholders impacted by the Regulations is foreseen at least for 3 years. Targeted factsheets are produced for each target and the webpages of DG GROW on medical devices will be updated to provide more accurate and updated information. | Updated information to be provided during the transitional period of the Regulations. Examples of deliverables are information factsheets, targeted presentations, dedicated website. | The first factsheets have been put on the current DG GROW webpages on medical devices in July 2018. Three additional factsheets have been finalised in November 2018 for publication. The new website will be put on line in December 2018.
8 | Expert advisory structure: Setting of MDCG | Article 103 MDR | Setting of MDCG as an expert group of the European Commission. MDCG, composed by MS experts and chaired by the Commission, provides advice on all matters related to the implementation of the Regulation. | 26 November 2017 (Legal deadline) | Established by the legal deadline COMPLETED
9 | Expert advisory structure: Setting of MDCG subgroups | Article 103 MDR | Setting of MDCG sub-groups, providing MDCG with the necessary expertise in relation to specific fields. | To be completed by Q1 2019 | Launch of the call for applications for stakeholders launched with deadline expired on 15 November 2018. Formal establishment of the MDCG subgroups expected Q1 2019.
10 | Mandate to SCHEER on phthalates | Annex I Section 10.4.3 MDR | Mandate to the scientific Committee (SCHEER) to prepare guidelines on phthalates | 26 May 2018 (Legal deadline) | COMPLETED in September 2017. SCHEER's opinion expected in mid-2019
11 | EU medical device nomenclature | Article 26 MDR and 23 IVDR | Designation of the future EU medical device nomenclature to be used in the UDI database | Decision is expected by Q1 2019 | A task-force composed of Commission and Member States has been established. On the basis of an MDCG paper (accessible on DG GROW website), laying down the expected requirements of the future nomenclature, the task-force has completed its work in November 2018 and produced a report which was discussed by MDCG on 30 November.
12 | Standardisation mandate | Article 10 of Regulation (EU) No 1025/2012 (the 'Standardisation Regulation') | Request to the European Standardisation Organisations for development of standards in the field of medical devices - the existing standards harmonised under Medical Device Directives need to be aligned to the new framework. | Decision is expected by Q1 2019 | Consultation of MS on the scope of the first mandate ongoing.